## Executive Summary
KPIs
Total Builds | 33
Passed | 12
Failed | 20
CBT Issues | 13
Project | Total | Pass | Fail | Warning | CBT Issues | Software Issues
P768 | 21 | 7 | 13 | 0 | 12 | 0
BT1XX_GEN1_5 | 2 | 2 | 0 | 0 | 0 | 0
WS_GEN2 | 5 | 0 | 5 | 0 | 0 | 2
WL_GEN1_5 | 1 | 0 | 1 | 0 | 1 | 0
LB | 1 | 1 | 0 | 0 | 0 | 0
DT | 1 | 1 | 0 | 0 | 0 | 0
KM_KX_EJ | 2 | 1 | 1 | 0 | 0 | 1

## Build Details
SNO | Build Number | Project | Product | Region | Customer | Domain | Location | Mode | Test Bench | Branch | Start Time | Runtime (min) | Overall Result | Pass TC | Fail TC | Warn TC | Failure Reason (AI) | Confidence Score | Analysis Stage
1 | 1468697 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-02 03:05:57 | 52.8 | PASS | 24 | 1 | 0 | - | - | -
2 | 1468608 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 20:00:13 | 3 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
3 | 1468538 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 18:04:17 | 3 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
4 | 1468519 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-09-01 16:07:14 | 103.1 | FAIL | 0 | 25 | 0 | Multiple Issues (SW + CBT) | 85 | mixed
5 | 1468548 | BT1XX_GEN1_5 | IBC | NA | GM | N/A | N/A | iqm | HDRC01222 | BT1XX_PREINT | 2026-09-01 17:14:05 | 20.6 | PASS | 18 | 0 | 0 | - | - | -
6 | 1468532 | BT1XX_GEN1_5 | IBC | NA | GM | N/A | N/A | iqm | HDRC01222 | BT1XX_PREINT | 2026-09-01 16:22:11 | 29.3 | PASS | 18 | 0 | 0 | - | - | -
7 | 1468480 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 15:07:22 | 44.1 | PASS | 24 | 1 | 0 | - | - | -
8 | 1468412 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 13:50:05 | 45.1 | FAIL | 23 | 2 | 0 | Review Required | 0 | error
9 | 1468213 | WS_GEN2 | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC01580 | MY27.5_WS_ICE_PreInteg_SW | 2026-09-01 12:49:19 | 48.8 | FAIL | 21 | 6 | 0 | Software Issue | 80 | llm
10 | 1467710 | P768 | IBC | NA | FORD | N/A | N/A | nightly | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-09-01 12:28:03 | 66.8 | PASS | 24 | 19 | 0 | - | - | -
11 | 1467784 | WS_GEN2 | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC01580 | MY27.5_WS_ICE_PreInteg_SW | 2026-09-01 09:08:14 | 46.3 | FAIL | 21 | 6 | 0 | Review Required | 0 | error
12 | 1467766 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 08:13:32 | 46.6 | PASS | 24 | 1 | 0 | - | - | -
13 | 1467311 | WL_GEN1_5 | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC01281 | MY27_WL_V39.0_Baseline_MainInteg | 2026-09-01 07:30:07 | 46.8 | FAIL | 0 | 25 | 0 | CBT Issue | 95 | deterministic
14 | 1467719 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-09-01 07:06:47 | 50.6 | PASS | 24 | 1 | 0 | - | - | -
15 | 1467700 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 02:50:31 | 2 | N/A | 0 | 1 | 0 | - | - | -
16 | 1467639 | P768 | IBC | NA | FORD | N/A | N/A | nightly | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 02:18:55 | 8 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
17 | 1467637 | P768 | IBC | NA | FORD | N/A | N/A | nightly | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 01:59:11 | 8 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
18 | 1467629 | WS_GEN2 | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC01580 | MY27.5_WS_ICE_PreInteg_SW | 2026-09-01 01:09:37 | 48 | FAIL | 21 | 6 | 0 | Review Required | 0 | error
19 | 1467638 | P768 | IBC | NA | FORD | N/A | N/A | nightly | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 01:39:02 | 8.1 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
20 | 1467568 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-09-01 00:41:34 | 8 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
21 | 1467392 | P768 | IBC | NA | FORD | N/A | N/A | formal | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-09-01 00:21:43 | 8 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
22 | 1467391 | P768 | IBC | NA | FORD | N/A | N/A | formal | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-09-01 00:01:47 | 8.1 | FAIL | 0 | 1 | 0 | CBT Issue | 95 | deterministic
23 | 1467501 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-08-31 21:54:40 | 113.1 | FAIL | 0 | 25 | 0 | Multiple Issues (SW + CBT) | 85 | mixed
24 | 1467530 | LB | PBM | NA | STELLANTIS | N/A | N/A | iqm | HDRC01301 | STL_LB_IBC_ICE_MY28_XV02.1_Integ | 2026-08-31 21:50:23 | 34.1 | PASS | 17 | 4 | 0 | - | - | -
25 | 1467485 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-08-31 20:44:16 | 56.1 | FAIL | 23 | 2 | 0 | Suspected CBT Issue | 80 | llm
26 | 1467482 | DT | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC60125 | PREINTEG_STLA_DT_IBC_ICE_AR_ICC | 2026-08-31 20:12:50 | 47.3 | PASS | 26 | 2 | 0 | - | - | -
27 | 1467390 | P768 | IBC | NA | FORD | N/A | N/A | formal | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-08-31 19:03:42 | 85 | FAIL | 21 | 22 | 0 | Multiple Issues (SW + CBT) | 85 | mixed
28 | 1467363 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_PREINTEG_FORD_P768_IBC_VTx_B | 2026-08-31 17:52:57 | 55.1 | PASS | 24 | 1 | 0 | - | - | -
29 | 1467337 | P768 | IBC | NA | FORD | N/A | N/A | iqm | HDRC01578 | IQM_INTEG_FORD_P768_IBC_VTx_B | 2026-08-31 16:40:56 | 55.9 | PASS | 24 | 1 | 0 | - | - | -
30 | 1467214 | WS_GEN2 | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC01580 | MY27.5_WS_ICE_PreInteg_SW | 2026-08-31 14:17:25 | 47.3 | FAIL | 21 | 6 | 0 | Review Required | 0 | error
31 | 1467139 | KM_KX_EJ | PBM | NA | STELLANTIS | N/A | N/A | iqm | HDRC01301 | MY27_KM_PRE_INTEG | 2026-08-31 12:59:59 | 38.5 | PASS | 21 | 0 | 0 | - | - | -
32 | 1466760 | KM_KX_EJ | PBM | NA | STELLANTIS | N/A | N/A | iqm | HDRC01301 | MY27_KM_PRE_INTEG | 2026-08-31 10:48:59 | 30 | FAIL | 1 | 2 | 0 | Software Issue | 80 | llm
33 | 1466949 | WS_GEN2 | IBC | NA | STELLANTIS | N/A | N/A | iqm | HDRC01580 | MY27.5_WS_ICE_PreInteg_SW | 2026-08-31 10:38:01 | 31.1 | FAIL | 1 | 2 | 0 | Software Issue | 80 | llm

## AI Failure Analysis
Build Number | Project | Product | Region | Mode | Fault Category | Failed Testcases | AI Analysis
1468608 | P768 | IBC | NA | iqm | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1468538 | P768 | IBC | NA | iqm | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1468519 | P768 | IBC | NA | iqm | Multiple Issues (SW + CBT) | - Perform Flashing using DET Tool - Check Bus Communication - Read Identification Data - Calibration Routines - Clear DTC Startup - ECU Diagnostic Reset - All Diagnostic Sessions Test - ECU Sleep Test - ECU Wakeup Test - Measurement Startup Time - Enable XCP - Read Stack Usage - Read CPU Load - Under Voltage Test - Read DTC - Check Absolute Cycle Time - Check Relative Cycle Time - Check Message Relative Occurrence Violation - Evaluate DTC - Clear DTC - Read Customer and Internal Faults - WSS Disconnection fault Test - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - Re-Flashing using DET Tool | 1. [SW] The test intent was to perform flashing using the DET tool, but it failed due to unexpected return codes and communication failures on multiple CAN channels. ¦ 2. [CBT] CAN/Diagnostic — Communication Error in testcase 'Read Identification Data'. Evidence: "Could not send request for BootSoftwareIdentificationData 22 F1 80 !". 22 subsequent testcase(s) cascaded.
1468412 | P768 | IBC | NA | iqm | Review Required | - Read CPU Load - Check Absolute Cycle Time | AI parse failed.
1468213 | WS_GEN2 | IBC | NA | iqm | Software Issue | - Evaluate DTC - Read Customer and Internal Faults - ABS Maneuver - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - EPB Apply Release With Diag | The test intent was to evaluate DTCs, but the ECU failed to provide expected results. This indicates a software defect in the ECU logic.
1467784 | WS_GEN2 | IBC | NA | iqm | Review Required | - Evaluate DTC - Read Customer and Internal Faults - ABS Maneuver - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - EPB Apply Release With Diag | AI parse failed.
1467311 | WL_GEN1_5 | IBC | NA | iqm | CBT Issue | - Flash Application with SerialLoader - Calibration Routines - Read Lamp Status - Variant Coding - Clear DTC Startup - ECU Diagnostic Reset - All Diagnostic Sessions Test - Read Identification Data - Check Bus Communication - ECU Sleep Test - ECU Wakeup Test - Measurement Startup Time - Invalid Faults Test - Signal Valid Range Test - Timeout Faults Test - Under Voltage Test - Read DTC - Evaluate DTC - Clear DTC - Read Customer and Internal Faults - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - WSS Disconnection fault Test - Low Speed Test - Re-Flash Application with SerialLoader | Root cause: UDS Tool — Session Failure in testcase 'Flash Application with SerialLoader'. Evidence: "Could not send request for ActiveDiagnosticSession !". 24 subsequent testcase(s) cascaded. Action: Assign to bench maintenance.
1467639 | P768 | IBC | NA | nightly | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1467637 | P768 | IBC | NA | nightly | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1467629 | WS_GEN2 | IBC | NA | iqm | Review Required | - Evaluate DTC - Read Customer and Internal Faults - ABS Maneuver - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - EPB Apply Release With Diag | AI parse failed.
1467638 | P768 | IBC | NA | nightly | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1467568 | P768 | IBC | NA | iqm | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1467392 | P768 | IBC | NA | formal | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1467391 | P768 | IBC | NA | formal | CBT Issue | - Perform Flashing using DET Tool | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance.
1467501 | P768 | IBC | NA | iqm | Multiple Issues (SW + CBT) | - Perform Flashing using DET Tool - Check Bus Communication - Read Identification Data - Calibration Routines - Clear DTC Startup - ECU Diagnostic Reset - All Diagnostic Sessions Test - ECU Sleep Test - ECU Wakeup Test - Measurement Startup Time - Enable XCP - Read Stack Usage - Read CPU Load - Under Voltage Test - Read DTC - Check Absolute Cycle Time - Check Relative Cycle Time - Check Message Relative Occurrence Violation - Evaluate DTC - Clear DTC - Read Customer and Internal Faults - WSS Disconnection fault Test - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - Re-Flashing using DET Tool | 1. [SW] The test intent was to perform flashing using the DET tool, but it failed due to unexpected return codes and communication failures on multiple CAN channels. ¦ 2. [CBT] CAN/Diagnostic — Communication Error in testcase 'Read Identification Data'. Evidence: "Could not send request for BootSoftwareIdentificationData 22 F1 80 !". 22 subsequent testcase(s) cascaded.
1467485 | P768 | IBC | NA | iqm | Suspected CBT Issue | - Read CPU Load - Clear DTC | The test intent was to measure CPU load and clear DTCs, but the failure pattern is ambiguous with no recognizable ECU signature.
1467390 | P768 | IBC | NA | formal | Multiple Issues (SW + CBT) | - ECU Sleep Test - ECU Wakeup Test - Read CPU Load - Check Absolute Cycle Time - Check Message Relative Occurrence Violation - Dyno Mode Entry via CAN Command - Dyno Mode Entry and Exit via CAN Command - Dyno Mode Entry via CAN Command and Exit via Missing CAN Message - Dyno Mode Entry via CAN Command and Exit via Faulted WSS - Dyno Mode Entry via CAN Command and Exit via Ignition Off - Dyno Mode Entry via CAN Command and Exit via Ignition Missing Message - Dyno Mode Entry via CAN Command and Exit via Faulty Yaw Flag - Dyno Mode Entry via CAN Command and Exit via Sustained Yaw Flag - Dyno Mode Entry via CAN Command and Exit via NoData Yaw Flag - Dyno Mode Entry via DID Command - Dyno Mode Entry and Exit via DID Command - Dyno Mode Entry via DID Command and Exit via WSS Fault - Dyno Mode Entry via DID Command and Exit via Faulty Yaw Flag - Dyno Mode Entry via DID Command and Exit via No Data Yaw Flag - Dyno Mode Entry via DID Command and Exit via Yaw Flag - Dyno Mode Entry via NVRAM CAN Command - Dyno Mode Entry via NVRAM DID Command | 1. [SW] AI parse failed. ¦ 2. [CBT] Vector Simulation Node — Missing in testcase 'Dyno Mode Entry via CAN Command and Exit via Missing CAN Message'. Evidence: "No message 'FD1_CAN_1::VectorSimulationNode::EngineClimateData_oFD1_CAN' could be found.". 14 subsequent testcase(s) cascaded.
1467214 | WS_GEN2 | IBC | NA | iqm | Review Required | - Evaluate DTC - Read Customer and Internal Faults - ABS Maneuver - Interrupt ECU sleep process - Check ECU State after Multiple Hard Reset - EPB Apply Release With Diag | AI parse failed.
1466760 | KM_KX_EJ | PBM | NA | iqm | Software Issue | - Flash Application with SerialLoader - Flash Application with Memtool | The test intent was to flash an application file using the SerialLoader, but the flashing process failed.
1466949 | WS_GEN2 | IBC | NA | iqm | Software Issue | - Flash Application with SerialLoader - Flash Application with Memtool | The test intent was to flash an application file using the SerialLoader, but the flashing process failed.

## CBT Issue Register
Build Number | Project | Product | Region | Test Bench | Fault Category | AI Root Cause Analysis | Action Required
1468608 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1468538 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467311 | WL_GEN1_5 | IBC | NA | HDRC01281 | CBT Issue | Root cause: UDS Tool — Session Failure in testcase 'Flash Application with SerialLoader'. Evidence: "Could not send request for ActiveDiagnosticSession !". 24 subsequent testcase(s) cascaded. Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467639 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467637 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467638 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467568 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467392 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467391 | P768 | IBC | NA | HDRC01578 | CBT Issue | Root cause: DET Tool — Firmware Flash Failure in testcase 'Perform Flashing using DET Tool'. Evidence: "DET Flashing failed after all retries.". Action: Assign to bench maintenance. | Assign to Bench Maintenance
1467485 | P768 | IBC | NA | HDRC01578 | Suspected CBT Issue | The test intent was to measure CPU load and clear DTCs, but the failure pattern is ambiguous with no recognizable ECU signature. | Assign to Bench Maintenance